## Sheet1
Risk | Outcome | Responsibility | Impact | Likelihood | Risk Factor | Control/Mitigation | Mitigated Impact | Mitigated Risk | Mitigated Risk Factor
Permissions do not work properly | Users and guests have admin or user privileges, and can access admin or user data | Developers | 5 | 1 | 5 | Permissions related to authentication, live test permissions | 5 | 0 | 0
Cookies save sensitive data | Cookies could be accessed by malicious JS scripts inserted into forms, and sensitive data used for fraud | Developers | 5 | 2 | 10 | Validate form data, make sure cookies only store non-sensitive data | 3 | 1 | 3
User details not correctly stored | Huge fine for breaking regulations | Developers | 5 | 2 | 10 | Ensure all data stored in accordance w regulations | 5 | 0 | 0
Access to database | sensitive/important data altered or accessed | User/Developer | 4 | 4 | 16 | Ensure permissions are correct | 4 | 0 | 0
Duplicate user data | Higher costs | User/Developer | 2 | 4 | 8 | If records are the same prevent the form inserting into database | 2 | 1 | 2
Spam accounts created | Higher costs, abuse on discussion boards | User | 3 | 4 | 12 | Buy third party software to deal with it | 2 | 1 | 2
Payment details not secured | Fraud, fines for not securing details | Developers | 4 | 1 | 4 | Follow appropriate regulations and encrypt data | 4 | 0 | 0
Routes not appropriately coded | Customers sent to wrong parts of site | Developers | 1 | 3 | 3 | Live test routes | 1 | 0 | 0
Forms allow falsey data | Could break database or backend | User/Developer | 5 | 3 | 15 | Live testing, data validation | 5 | 0 | 0
Users abuse each other on discussion board | Hate crimes, cyber bullying, damage to site reputation | User | 3 | 5 | 15 | Prevent anonymous sign up, use third party modules or software, use moderators, impelement language filter | 3 | 1 | 3
Forms allow files | Malicious software injections | User/Developer | 5 | 3 | 15 | Prevent special characters in certain inputs | 4 | 1 | 4
Faulty React/HTML code | Site loads slowly, has poor functionality or breaks | Developers | 4 | 2 | 8 | Live test code | 3 | 1 | 3
Incorrect datatypes allowed in forms | Back end breaks, data not stored even if site says it is | Developers | 5 | 2 | 10 | Data validation/normalisation when converting form data to JSON | 4 | 0 | 0
Schema doesn't cover all collections | Poor data stored, unnormalised data taking up space, incorrect data types could break code | Developers | 4 | 1 | 4 | Check over schema, if alterations to classes/structure, make changing schema part of process | 3 | 0 | 0
Application goes offline | The site can't be reached | Developer/ISP | 5 | 1 | 5 | Make sure internet connection is stable, ensure server is running before application launch | 1 | 3 | 3
Unoptimised database | Can slow app and crash if under high usage loads | Developers | 4 | 1 | 4 | Use file statistics and scripts to identify inefficient queries | 2 | 1 | 2
Major changes in development environment or dependencies | Parts of the code may not work, app may crash | Software manufacturers | 5 | 3 | 15 | Constantly checking for major updates and updating code to match | 5 | 1 | 5
Hardware issues | Code inaccessible | Developer, Hardware manufacturers | 4 | 1 | 4 | Ensure codebase is securely stored on cloud | 1 | 0 | 0
Source Control issues | Code cannot be saved to repository, vulnerable to hardware issues | Source control provider | 5 | 1 | 5 | Ensure local repository is shareable, have backup repository on another service | 3 | 1 | 3
Database hacked | Stolen data, fraud | Security team, cloud provider | 5 | 1 | 5 | Update credentials for DB access regularly, ensure cloud provider rules are being followed | 5 | 1 | 5